## Introduction
Participant Monthly Report
A)Report Sections:
This form contain the following sections: |  |  |  | Participant Stakeholder input R: Review and Approve, P: Prepare, I: Informed
Section/SR | Worksheet name | Description |  | Participant Representative | Project Manager (PMC) | Consultant | Contractor
I | Monthly Report Statistics | This section has the statistical data which are assessed to rate the variable areas of the project performance (only columns F and G and with grey color to be filled as indicated in each cell)●. These data include: -Summary Narratives -Design Summary -Construction Summary -Issues / interface and NCR status -Health Safety and environment (Please note that cumulative figures are for info only) -Worker Welfare |  | I | R | R/P | P
II | Monthly Report Scheduling | This section includes the high level updates of actual vs plan data and must be supported with an updated P6 resource loaded schedule. (Cells with grey color need to be filled as indicated in each cell)●. These data include: -Overall progress -Construction Progress by WBS -Milestones Update -Final Inspections Approval Status -S-curve and Histogram Data -Progress Photos |  | I | R | R | P
III | Sustainability Score aggregator | This section contains the data entries for sustainably for the reporting period (Cells with grey color need to be filled as indicated in each cell)● |  | I | I | R/P | P
IV | Dashboard Report | This section is automatically generated upon the entry of the data in the above sections. |  | I | I | I | I
| Insert text | ●Only these cells need to be filled as indicated in each
B)Report Supporting documents: (to be submitted with the report):
SR | Document name / Reference | Description |  | Participant Rep | Project Manager (PMC) | Consultant | Contractor
V | (A)-Worker Welfare Improvement Action Plan 05007-TLK-P990000-WW-000013(1) | As included in WW package under step 3 - (improvement action plan). The actions identified shall be updated monthly and submitted along the monthly report. |  | I | R | R | P
VI | Contractor Environment Logs SB 05007-TLK-P990000-EN-000050(1) | Please follow the submittal instructions on the document |  | I | I | R | P
VII | (A)-Baseline schedule (with the first report) | (A)-For the first submission (or in case of Baseline revision), a package of baseline supporting documents need to be submitted as detailed below. Any revision or changes to the Baseline needs to be notified to the organiser in advance to the report submission. Supporting Documents for the baseline submission: ● Native format of schedule in addition to the PDF file indicting early and late dates with the total float. ● Driven by logic milestones for the following major events: 1. Shell and core completion 2- Readiness for authority inspection 3- Building certificate completion 4- Operation fitness certificates ● Driven by logic milestones for the interim events such as: sub-structure completion, façade works completion, super structure works, tower crane dismantling, wild air on, power on, etc. ● Construction Weightage distribution for the progress measurement as per the activity types defined with the organiser WBS; please refer to part 2 under section II of this report ● Print out of baseline Critical Path ● Narrative detailing the project and the execution plan. ● Zoning plan aligned with schedule subdivisions. ● Manpower Histogram, commodities histogram, and planned S-curve. |  | I | R | R | P
| (B)-Updated P6 resource loaded schedule | (B)-Native P6 format of the schedule update to demonstrate the data reported in section II from this report. Also, two PDF files: ● Indicting planned, actual dates, percent complete with the total float and showing Gantt chart with Baseline assigned. ● An updated critical path of the project |  | I | R | R | P
C) Participant's Red-Amber-Green (RAG) Criteria:
| Function | Metric | Criteria |  |  |  | RAG Status
| Health and Safety | Participant performance based incident performance and leading pillars indicators. | Incident performance is RED OR All Pillars are RED OR Incident performance is AMBER and 3 pillars are RED |  |  |  | Red
|  |  | Incident performance is GREEN AND ≥2 leading pillars indicators are RED OR Incident performance is AMBER AND <2 leading pillars indicators are RED |  |  |  | Amber
|  |  | Incident performance is GREEN AND ≤1 leading pillar is RED |  |  |  | Green
| Environment | Participant Environmental Incident (serious) Frequency Rate per 100,000 hours | ≤ 0.02 |  |  |  | Green
|  |  | 0.02 < X ≤ 0.04% |  |  |  | Amber
|  |  | > 0.04 |  |  |  | Red
| Sustainability | Sustainability Score as per weightages (Amber is 50% of the score) | if X ≥ 75% |  |  |  | Green
|  |  | 75%< X ≤50% |  |  |  | Amber
|  |  | If X < 50% |  |  |  | Red
| Worker Welfare | Number of serious violations and status of action improvement plans | No open Serious non-Compliance and ≤10 non-compliances with overdue closure date |  |  |  | Green
|  |  | No open Serious non-Compliance and >10 non-compliances with overdue closure date |  |  |  | Amber
|  |  | One open Serious non-Compliance with overdue closure date |  |  |  | Red
| Participant progress (Construction) | Participant forecast milestones completion and construction progress variance | Meeting all milestones |  |  |  | Green
|  |  | Not meeting interim milestones by 2 weeks or more with less than 10% construction progress variance OR Not meeting major finish milestones by less than 2 weeks |  |  |  | Amber
|  |  | Not meeting major finish milestones by 2 weeks or more OR Not meeting construction interim milestones by 2 weeks or more variance with more than 10% construction progress variance |  |  |  | Red
| Participant progress (Design) | Participant schedule variance from baseline for design submissions and ultimately building permit request submission | ≤2 Weeks variance |  |  |  | Green
|  |  | 2< X ≤3 weeks variance |  |  |  | Amber
|  |  | >3 weeks variance |  |  |  | Red

## I. Monthly Report Statistics
Participant: |  | Please fill in
Reporting Period: |  | Please fill in
Project Manager (PMC): |  | Please fill in
Supervision Consultant: |  | Please fill in
Architect of Record (AOR): |  | Please fill in
Main Contractor: |  | Please fill in
Plot reference: |  | Please fill in
Date: |  | 2019-10-22
Function | Statistics | Activity |  | Value (current month) | Value (Cumulative) | Metric / Reference | Red-Amber-Green Status | Type of Field / Parameters explanation
1. Summary Narratives |  | 1.1. Executive Summary |  | Insert text |  | Narrative on the project status including information on key stages |  | Text field
|  | 1.2. Summary of Health and Safety |  | Insert text |  | Narrative detailing high level summary of health and safety performance including incident performance, trends, KPI performance, actions required, best practice and lessons learned |  | Text field
|  | 1.3. Summary of Environment |  | Insert text |  | Narrative detailing high level summary of environment performance CEMP/CWMP audits and findings |  | Text field
|  | 1.4. Summary of Worker Welfare |  | Insert text |  | Narrative detailing high level summary of worker welfare performance |  | Text field
|  | 1.5. Summary of Sustainability |  | Insert text |  | Narrative on the sustainability performance based on the data log in sheet III |  | Text field
2. Design Summary |  | 2.1. Concept Design status |  | Select from Drop Down List |  | Status of Latest Concept Design Submittal |  | Drop down
|  | 2.2. Design change |  | Select from Drop Down List |  | Status of Latest Design Change Request Submittal |  | Drop down
|  | 2.3. Final Design Status |  | Select from Drop Down List |  | Status of Latest Final Design Submittal if any |  | Drop down
|  | 2.4. Building Permit |  | Select from Drop Down List |  | Status of Building Permit Request |  | Drop down
3. Construction Summary |  | 3.1. Requests
|  | 3.1.1. Plot Possession | Approved | Insert number |  | Input the number of approved plot possession requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of plot possession requests awaiting approval |  | Number field
|  | 3.1.2. Lay Down Area | Approved | Insert number |  | Input the number of approved Lay Down Area requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of Lay Down Area requests awaiting approval |  | Number field
|  | 3.1.3. Design Changes | Approved | Insert number |  | Input the number of approved Design Changes requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of Design Changes requests awaiting approval |  | Number field
|  | 3.1.4. New Contractor | Approved | Insert number |  | Input the number of approved requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of requests awaiting approval |  | Number field
|  | 3.1.5. Hoarding Removal | Approved | Insert number |  | Input the number of approved requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of requests awaiting approval |  | Number field
3.2. Permits
|  | 3.2.1. Enabling Works | Approved | Insert number |  | Input the number of approved requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of requests awaiting approval |  | Number field
|  | 3.2.2. Building Permit | Approved | Insert number |  | Input the number of approved requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of requests awaiting approval |  | Number field
|  | 3.2.3. Inspections | Approved | Insert number |  | Input the number of approved requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of requests awaiting approval |  | Number field
|  | 3.2.4. Building completion certificate | Approved | Insert number |  | Input the number of approved requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of requests awaiting approval |  | Number field
|  | 3.2.5. Fitness Operational Certificate | Approved | Insert number |  | Input the number of approved requests |  | Number field
|  |  | Waiting for Approval | Insert number |  | Input the number of requests awaiting approval |  | Number field
|  | 3.3.1 Construction Narrative | This month achieved activities | Insert text |  | Narrative detailing high level summary of construction activities achieved during the reporting period and planned for the next one. Please make sure to include - with specific dates - major events which need coordination. |  | Number field
|  |  | Next month planned activities | Insert text |  |  |  | Number field
Issues / interface and NCR status | 4.1 Key issues related to the Organiser and third parties | 4.1 Key Issues |  | Insert text |  | Input key open issues that requires escalation to Expo2020 Organiser |  | Text field
| 4.2 Actions needed | 4.2 Actions |  | Insert text |  | Input the actions needed to resolve the issues |  | Text field
| 5. Known interface with work outside plot | 5.1. Design Interfaces |  | Insert text |  | Input key design interfaces with Expo2020 Organiser |  | Text field
|  | 5.2. Construction Interfaces |  | Insert text |  | Input key construction interfaces with Expo2020 Organiser |  | Text field
| 6. Status NCR | 6. Number of NCRS in the reporting period | Raised NCRS | N/A | Insert number | Input the number of raised NCRs during the reporting period |  | Number field
|  |  | Open NCRS | N/A | Insert number | Input the number of open NCRs during the reporting period |  | Number field
|  |  | Closed NCRS | N/A | Insert number | Input the number of Successfully closed during the reporting period |  | Number field
Health, Safety, and Enviroment | 7. Project Statistics | 7.1. Average Number of Personnel on-site During the Reporting Period |  | 0 | N/A | Average number of personnel on-site on the project during the reporting period (day/night shift, blue/white collar) (Main Contractor plus all levels of subcontractors). |  | Automatically calculated
|  | 7.1.1. Average White Collar Day Shift |  | Insert number | N/A |  |  | Number Field
|  | 7.1.2. Average White Collar Night Shift |  | Insert number | N/A |  |  | Number Field
|  | 7.1.3. Average Blue Collar Day Shift |  | Insert number | N/A |  |  | Number Field
|  | 7.1.4. Average Blue Collar Night Shift |  | Insert number | N/A |  |  | Number Field
|  | 7.2. Total Number of Work Hours (During the Reporting Period / and Cumulative to date) |  | Insert number | Insert number | The total number of hours worked by any person on-site on the project in the reporting period/and cumulative throughout the project life from the work commencement of the first contractor on site |  | Number Field
| 8. Incident Performance | 8.1. Serious Injuries - Fatalities |  | Insert number | Insert number | Total Number of Fatalities in the reporting period / cumulative to date Fatality = death of any person | #VALUE! | Number Field
|  | 8.2. Serious Injuries - Lost Time Injuries |  | Insert number | Insert number | Total Number of Lost Time Injuries in the reporting period / cumulative to date An injury arising out of, or in connection with work, which leads to an employee absence from work for more than three days in addition to the day of injury (LTI) |  | Number Field
|  | 8.3. Serious Injuries - Major Injuries |  | Insert number | Insert number | Total Number of Major Injuries in the reporting period / cumulative to date - Broken bones excluding fingers/toes and including fracture of the skull, spine, pelvis or any bone in the wrist, arm, leg or ankle - Amputation of a hand, arm, foot, finger, thumb or any body organ - Unconsciousness resulting from electric shock, heat stroke, lack of oxygen, etc. - Second or third degree burns because of any reason - Any other injury which results in the admission of an injured employee to hospital for more than 24 hours for medical treatment |  | Number Field
|  | 8.4. Minor Injuries - First Aid Case |  | Insert number | Insert number | Total Number of First Aid Cases in the reporting period / cumulative to date - Cleaning, flushing or soaking wounds on the surface of the skin - Using wound coverings such as bandages, Band-Aids™, gauze pads, etc.; or using butterfly bandages or Steri-Strips - Use of non-rigid means of support e.g. bandages, wraps, non-rigid back belts - Using hot or cold therapy or massages - Drinking fluids for relief of heat stress - Using a non-prescription medication at nonprescription strength - Administering tetanus immunizations - Using temporary immobilization devices while transporting an accident victim (e.g., splints, slings, neck collars, back boards, etc.) - Drilling of a fingernail or toenail to relieve pressure, or draining fluid from a blister - Using eye patches - Removing foreign bodies from the eye using only irrigation or a cotton swab - Removing splinters or foreign material from areas other than the eye by irrigation, tweezers, cotton swabs or other simple means - Using finger guards |  | Number Field
|  | 8.5. Minor Injuries - Restricted Work Case |  | Insert number | Insert number | Total Number of Restricted Work Cases in the reporting period / cumulative to date The employer or a licensed health care professional keeps an employee from performing one or more of the routine functions of his or her job, or from working the full workday that he or she would have otherwise been scheduled to work |  | Number Field
|  | 8.6. Minor Injuries - Medical Treatment Case |  | Insert number | Insert number | Total Number of Medical Treatment Case in the reporting perio / cumulative to date An injury that receives medical treatment by a third party medical provider and is more severe than first aid but does not result in restricted days or days away from work. Where evaluation is completed for the purpose of diagnosis this is not regarded as a Medical Treatment Injury |  | Number Field
|  | 8.7. Near Miss (Minor) |  | Insert number | Insert number | Total Number of minor Near Misses in the reporting period / cumulative to date An occurrence that under slightly different circumstances would be likely to result in a minor incident of a different incident type |  | Number Field
|  | 8.8. Near Miss (Serious) |  | Insert number | Insert number | Total Number of serious Near Misses in the reporting period / cumulative to date An occurrence that under slightly different circumstances would be likely to result in a major incident of a different incident type |  | Number Field
|  | 8.9. Property Damage (Minor) |  | Insert number | Insert number | Total Number of minor Property Damage in the reporting period / cumulative to date An incident including but not limited to plant and construction equipment, facilities, buildings and other tangible property resulting in minor damage that requires minimal cost or time to repair |  | Number Field
|  | 8.10. Property Damage (Serious) |  | Insert number | Insert number | Total Number of serious Property Damage in the reporting period / cumulative to date An incident including but not limited to plant and construction equipment, facilities, buildings and other tangible property resulting in significant damage |  | Number Field
|  | 8.11. Fire (Minor) |  | Insert number | Insert number | Total Number of minor Fire Incidents in the reporting period / cumulative to date A fire where the consequences result in no risk to the life and only minor risk or damage to property, e.g. fire in an outside area, local fire of an item of manned plant immediately extinguished or burned out, fire in an external smoking shelter |  | Number Field
|  | 8.12. Fire (Serious) |  | Insert number | Insert number | Total Number of serious Fire Incidents in the reporting period / cumulative to date Any fire where there was a risk to life or where there was significant damage to property, e.g. fire within a building, fire requiring evacuation of more than immediately local personnel |  | Number Field
|  | 8.13. RTA (Minor) |  | Insert number | Insert number | Total Number of minor RTA Incidents (within the Expo 2020 Site Boundary) in the reporting period / cumulative to date An incident where there is an impact with another vehicle or structure causing damage |  | Number Field
|  | 8.14. RTA (Serious) |  | Insert number | Insert number | Total Number of serious RTA Incidents (within the Expo 2020 Site Boundary) in the reporting period / cumulative to date A collision involving a motor vehicle being driven on site, or offsite on work related business, regardless of the type of vehicle (personal, leased, rental, borrowed, company-owned, etc) that results in personal injury or the vehicle being immobilised or requiring recovery |  | Number Field
|  | 8.15. Occupational Health (Minor) |  | Insert number | Insert number | Total Number of minor Occupational Health Incidents in the reporting period / cumulative to date Any mild exposure to an occupational hazard resulting in a skin condition or another minor outcome |  | Number Field
|  | 8.16. Occupational Health (Serious) |  | Insert number | Insert number | Total Number of serious Occupational Health Incidents in the reporting period / cumulative to date Any acute or chronic illnesses or diseases which may be caused by inhalation, absorption, ingestion or direct contact; exposure to chemical, biological or infections agents and radiological hazards; and/or stress |  | Number Field
|  | 8.17. Security (Minor) |  | Insert number | Insert number | Total Number of minor Security Incidents in the reporting period / cumulative to date Arson. Assault. Opportunity Crimes including minor thefts. Unauthorised vehicles in restricted areas. Deranged, unstable, discontented individual. Failure of essential services resulting in an impact on security systems |  | Number Field
|  | 8.18. Security (Serious) |  | Insert number | Insert number | Total Number of serious Security Incidents in the reporting period / cumulative to date Theft of a motor vehicle, attack to property causing damage requiring investment to replace. Theft of significant items of property. Trafficking, Smuggling. Industrial action, civil protest or unrest. Overcrowding of building spaces or immediate building footprint |  | Number Field
|  | 8.19. Environment (Minor) |  | Insert number | Insert number | Total Number of Minor Environmental Incidents in the reporting period / cumulative to date - Incidents that have or may cause minor harm or damage to the environment, and that are easily brought under control and prevented from re-occurring - Spillage: A spill of less than 200 litres of a hazardous liquid where the location is away from a sensitive receptor, the impact is immediately reversible and where spill response is immediately and successfully deployed. (EX20 and the Supervision Consultant reserve the right to request such incidents to be reclassified as serious where required) - Waste: unauthorised disposal of a small quantity of non-hazardous waste (quantity less than 1 ton) - Wastewater: Accidental overflow of minor quantities of wastewater from e.g. septic tanks or concrete washing bays (less than 200 litres) where the location is away from a sensitive receptor, the impact is immediately reversible and where cleaning response is immediately and successfully deployed - Receipt of a substantiated complaint associated with specific site activity - Minor nuisance but controllable and preventable from re-occurrence - Any other minor incident that occurs in an area of low sensitivity e.g. industrial area, hard standing, and where Small number and type of sensitive receptors affected - Minor harm to biodiversity or to non-endangered species of fauna / flora at the site |  | Number Field
|  | 8.20. Environment (Serious) |  | Insert number | Insert number | Total Number of Serious Environmental Incidents in the reporting period / cumulative to date - incidents which have caused catastrophic harm or damage to the environment e.g. requiring external involvement to clean-up, and therefore a high likelihood of regulatory action or other intervention by enforcing authority - Incidents that have or may cause significant or irreversible damage to the environment - Persistent non-significant breach or reoccurrence of the same minor incidents - Significant breach of the environment permit/license conditions - Fire, collapse, explosion or leakage of hazardous materials accidents accompanying with financial losses which lead to work suspension for a period more than one shift in one section of the worksite - Spillage: Significant spill within the site boundary where the quantity of material released to the environment exceeds 200 litres, even if not dangerous - Waste: unauthorised disposal of hazardous waste, disregarding the volume or quantity - Waste: unauthorised disposal of a large quantity of non-hazardous waste (quantity exceeding 1 ton) - Wastewater: unauthorised disposal of wastewater (Wastewater; Treated Sewage Effluent (TSE); Concrete wash water, or other), disregarding the volume or quantity - Wastewater: accidental overflow of large quantities of wastewater e.g. from septic tanks or concrete washing bays (more than 200 litres) - Excessive uncontrollable incidents which are likely to, or will re-occur to cause danger, nuisance, numerous complaints or significant impact to reputation - Massive loss of biodiversity at the site - Any other incident that occurs in sensitive areas (e.g. close to residential areas) and where large number and different type of sensitive receptors affected |  | Number Field
| 9. Leadership | 9. HSE Leadership Tour |  | Insert number | Insert number | The number of formal leadership tours carried out in the reporting period / cumulative to date A high level site inspection attended by one or more consultant or contractor senior manager or director to ensure that the necessary HSE provisions are in place. Please keep a Register with all your Leadership tours. ** Following fields are required in the register . Date, name of Leadership team, Area of the visit, extra information | 1 | Number Field RED : No tour has been completed GREEN : 1 or more tours have been completed
| 10. Communication | 10. Activity Briefing | Number of Attendees | Insert number | Insert number | The sum of attendees across all activity briefs during the reporting period / cumulative to date An activity based HSE briefing that communicates hazards, risks and control measures conducted at the start of a period of work or new task. | #VALUE! | Number Field RED #Attendees < ((average of blue collar workers (dayshift + nightshift)/Average number of personnel on-site during the reporting period)*total number of work hours during the reporting period)/11 GREEN #Attendees < ((average of blue collar workers (dayshift + nightshift)/Average number of personnel on-site during the reporting period)*total number of work hours during the reporting period)/11
| 11. Competency | 11. HSE Toolbox Talks |  | Insert number | Insert number | The number of toolbox talks completed in the reporting period / cumulative to date An informal briefing generally conducted on site to raise awareness or refresh knowledge of a particular HSE matter | 1 | Number Field RED : #TBT<=1 AMBER : 1 < #TBT < 4 GREEN : #TBTs >= 4
| 12. Engagement | 12.1. HSE Meeting |  | Insert number | Insert number | The number of health, safety and environment meetings undertaken in the reporting period / cumulative to date A meeting held by the contractor to review and discuss health, safety and environment matters | 1 | Number Field RED : #IMeetings<=1 AMBER : 1 < #Meetings < 4 GREEN : #Meetings >= 4
|  | 12.2. HSE Observations |  | Insert number | Insert number | The total number of observations recorded in the reporting period / cumulative to date An observation of condition or behavior that is observed and recorded | #VALUE! | Percentage % RED % Observations < 50% of total number of personnel AMBER 50% < % Observation <100% GREEN % of observations >=100%
| 13. Reward & Recognition | 13. HSE Award – Team / Individual |  | Insert number | Insert number | The number of formal awards issued to teams or individuals in the reporting period / cumulative to date An award given to a team or individual who has achieved exemplary HSE performance, aligned to the Expo 2020 HSE values of care, respect or pride | 1 | Number Field RED : No awards have been given GREEN : 1 or more award have been given
| 14. Continual Improvement | 14.1. Weekly HSE Inspection |  | Insert number | Insert number | The total number of formal inspections undertaken in the reporting period / cumulative to date A formal and documented process undertaken to identify potential HSE hazards on site led by the consultant and attended by the contractor. | 1 | Number Field RED : #Inspections<=1 AMBER : 1 < #Inspections < 4 GREEN : #Inspections >= 4
|  | 14.2. Consultant HSE Focus Audit |  | Insert number | Insert number | The number of focus audits undertaken in the reporting period / cumulative to date An in-depth audit of a particular and relevant HSE topic undertaken by the consultant | 1 | Number Field RED : 0 focus audits have been completed GREEN : 1 or more focus audits have been completed
|  | 14.3. Consultant Health & Safety Systems Audit |  | Insert number | Insert number | The number of health and safety systems audits conducted in the reporting period / cumulative to date A formal, systematic examination of health & safety management arrangements to evaluate compliance with Expo 2020 Assurance standards undertaken of the contractor by the consultant |  | Number Field
|  | 14.4. Consultant Environment Audit |  | Insert number | Insert number | The number of environment audits conducted in the reporting period / cumulative to date A formal, systematic examination of environment management arrangements to evaluate compliance with Expo 2020 Assurance standards undertaken of the contractor by the consultant |  | Number Field
|  | 14.5. Total number % of findings overdue |  | N/A | 0% | The cumulative % of HSE items or findings from audits that are overdue The total number of findings overdue divided by the total number of findings raised on the project to date as a percentage. | 1 | Percentage % RED % of overdue actions > 20% AMBER 10 < % of overdue actions <=20% GREEN % of overdue actions <=10%
15. Worker Welfare |  | 15.1. Total Serious Non-Compliances |  | N/A | 0 | Total Number of Open Serious Non-Compliances (15..1.1 + 15.1.2) |  | Automatically calculated
|  | 15.1.1. Open Serious Non-Compliances (Not Overdue) |  | N/A | Insert number | The number of current open serious non-compliances with the Main Contractor Direct Workforce (i.e. excludes subcontractor non-compliances), with or without action plans, and not yet due for close-out. |  | Number
|  | 15.1.2. Overdue Serious Non-Compliances |  | N/A | Insert number | The number of current open serious non-compliances with the Main Contractor Direct Workforce (i.e. excludes subcontractor non-compliances), with or without action plans, and overdue for close-out. |  | Number
|  | 15.2. Target Date to Close-Out all Open Serious Non-Compliances |  | N/A | DD-MM-YY | The date at which the Main Contractor has committed to close-out all current Open Serious Non-Compliance. |  | Date
|  | 15.3. Closed Serious Non-Compliances in period |  | Insert number | N/A | The number of Main Contractor serious non-compliances Closed in the reporting period. |  | Number
|  | 15.4. New Serious Non-Compliances in period |  | Insert number | N/A | The number of Main Contractor serious non-compliances discovered in the reporting period. |  | Number
|  | 15.5. Number of Serious WW Incidents reported in period |  | Insert number | N/A | Serious WW Incidents (as defined within the Expo Worker Welfare Standards, Section 3.13 b) reported within the period. |  | Number
|  | 15.6. WW Audits conducted by Supervision Consultant |  | Insert number | N/A | The number of Prequalification Assessments (PQA) and/or Compliance Audits (CA) checklists conducted and fully completed by the Supervision Consultant. |  | Number
|  | 15.7. WW Issue Log Reviews conducted by Supervision Consultant |  | Insert number | N/A | The number of times within the reporting period that the Supervision Consultant has reviewed all entries on the Main Contractors WWW issue Log. |  | Number
|  | 15.8. Number of Supervision Consultant's Full Time Equivalents (FTE) assigned to Worker Welfare |  | Insert number | N/A | Express the FTE value of Supervision Staff (or sub-consultants) assigned to conduct worker welfare monitoring and auditing of the Main Contractor(s). |  | Number (one decimal place e.g. 1.5)
|  | 15.9. WW Audits conducted by Contractor |  | Insert number | N/A | The number of Compliance Audits (CA) checklists conducted and fully completed by the Main Contractor on itself. |  | Number
|  | 15.10. WW Audits conducted on subcontractors/manpower providers |  | Insert number | N/A | The number of Prequalification Assessments (PQA) and/or Compliance Audits (CA) checklists conducted and fully completed by the Main Contractor on its subcontractors. |  | Number
|  | 15.11. New subcontractors appointed this period |  | Insert number | N/A | The number of newly appointed subcontractors in the period (i.e. Contract Awards). |  | Number
|  | 15.12. Subcontractors off-hired this period |  | Insert number | N/A | The number of disengaged subcontractors for this period. |  | Number
|  | 15.13. Currently onboard Subcontractors List |  | -Insert text -Insert text -Insert text |  | Please list in bullet points the current onboard subcontractors working in the project |  | Text field
|  | 15.14. Number of 'Newly Recruited' Blue Collar workers on Expo 2020 Site |  | Insert number | N/A | Total Number of Blue collar Workforce 'newly recruited' within the workforce numbers quoted above (Main Contractor plus all levels of subcontractors). |  | Number

## List (hidden)
Design Status
Not started | 01 - Mobilization
Not Applicable | 02 - Sub-Structure Works
In Progress | 03 - Super-Structure Works
Submitted for Approval | 04 - Shell and Core Completion
Approved | 05 - Façade
06 - Finishes and MEP
07 - External works
08- Testing and Commissioning
09 - Authorities Inspection
10 - Building Completion Certificate
11 - Operation Fitness Certificate

## II. Monthly Report Scheduling
Participant: | Please fill in
Reporting Period: | Please fill in
Project Manager (PMC): | Please fill in
Supervision Consultant: | Please fill in
Main Contractor: | Please fill in
Plot reference: | Please fill in
Date: | 2019-10-22
II. Monthly Report Scheduling (This summary must be supported with an updated P6 resource loaded schedule)
1. Overall progress
|  |  | Previous month |  | Cumulative |  |  | This Month ●
|  |  | Planned % | Actual % | Planned % | Actual % | Variance | Planned % | Actual %
Overall progress (automatically calculated from part 2) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
●Automatically calculated
2. Construction Progress by WBS
Current stage (please select from drop down list) :
01 - Mobilization
Construction WBS |  | Weight● | Previous month |  | Cumulative |  |  | This Month ● |  | 01 - Mobilization
|  |  | Planned % | Actual % | Planned % | Actual % | Variance | Planned % | Actual % | 02 - Sub-Structure Works
Mobilisation, Plot Pos, and Ground Works |  | 1.627% | Insert percentage | Insert percentage | Insert percentage | Insert percentage | #VALUE! | #VALUE! | #VALUE! | 03 - Super-Structure Works
Sub-Structure Works |  | 16.82% | Insert percentage | Insert percentage | Insert percentage | Insert percentage | #VALUE! | #VALUE! | #VALUE! | 04 - Shell and Core Completion
Super-Structure Works |  | 21.41% | Insert percentage | Insert percentage | Insert percentage | Insert percentage | #VALUE! | #VALUE! | #VALUE! | 05 - Façade
Façade |  | 12.23% | Insert percentage | Insert percentage | Insert percentage | Insert percentage | #VALUE! | #VALUE! | #VALUE! | 06 - Finishes and MEP
Finishes and MEP |  | 35.68% | Insert percentage | Insert percentage | Insert percentage | Insert percentage | #VALUE! | #VALUE! | #VALUE! | 07 - External works
External works |  | 6.116% | Insert percentage | Insert percentage | Insert percentage | Insert percentage | #VALUE! | #VALUE! | #VALUE! | 08- Testing and Commissioning
Testing and Commissioning |  | 6.116% | Insert percentage | Insert percentage | Insert percentage | Insert percentage | #VALUE! | #VALUE! | #VALUE! | 09 - Authorities Inspection
●The weightages provided are only for reference; resource loaded baseline weightages shall be incorporated | [9 empty] | 10 - Building Completion Certificate
[8 empty] | ●Automatically calculated |  | 11 - Operation Fitness Certificate
3. Milestones Update
Milestone |  |  |  |  | Baseline Milestone date | Forecast / Actual | Variance
Design/Permitting Interim Milestones | Concept Design Approval |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
| Final Design Approval |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
| Obtaining Plot Possession and Mobilising to site |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
| Obtaining Building Permit |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
Construction Interim Milestones | Shell and Core Completion (building weather tight) |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
| Readiness for Authorities Inspection |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
Main Major Milestones | Building Completion Certificate |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
| Operation Fitness Certificate |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
4. Final Inspections Approval Status
|  |  | Baseline Milestone date | Forecast / Actual | Variance
Security Industry Regulatory Agency (SIRA) |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
Dubai Municipality (DM) |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
Etisalat |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
Dubai Civil Defense (DCD) |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
Dubai Electricity and Water Authority (DEWA) - Water |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
Dubai South (DS) |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
Dubai Electricity and Water Authority (DEWA) - Electricity |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
5. S-curve and Histogram Data (please fill in months prior commencement dates with zero values)
| Manpower Histogram● |  | Progress
Month | Planned (Baseline) | Actual● | Cumulative Planned% (Baseline) | Cumulative Actual |  |  |  | Period Planned (Baseline) ● | Period Actual ●
2019-04-01 | Insert number | Insert number | Insert percentage | Insert percentage |  |  |  | Insert percentage | Insert percentage
2019-05-01 | Insert number | Insert number | Insert percentage | Insert percentage |  |  |  | #VALUE! | #VALUE!
2019-06-01 | Insert number | Insert number | Insert percentage | Insert percentage |  |  |  | #VALUE! | #VALUE!
2019-07-01 | Insert number | Insert number | Insert percentage | Insert percentage |  |  |  | #VALUE! | #VALUE!
2019-08-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2019-09-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2019-10-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2019-11-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2019-12-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2020-01-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2020-02-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2020-03-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2020-04-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2020-05-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2020-06-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2020-07-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2020-08-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
2020-09-01 | Insert number |  | Insert percentage |  |  |  |  | #VALUE!
●Please include only direct labors matching with the figure reported in (7.1.3 plus 7.1.4) under section I. column F of this report | [7 empty] | ●Automatically calculated
Important note: please be advised baseline data are to be pulled directly from the baseline resource loaded programme submitted with the first report. Any revision or changes to the baseline needs to be notified to the organiser in advance to the report submission
6. Progress Photos (please right click and then change picture for each of the below)

## III. Sust. Scores
Construction Sustainability KPI Aggregator
Notes: Please fill all green cells in each month and submit the completed spreadsheet for Expo programme-wide reporting. In Design Stage fill cells marked "D" for construction stage fill those marked "C"
Please fill in | Please fill in
KPI |  | Unit/Target |  | Parameters explanation | Red-Amber-Green Status
ENERGY
Reduce Energy Consumption (Design) |  |  |  | Notes:
Building energy | Baseline (ASHRAE 90.1-2013) | MWh/year |  | Use an energy modeling software (e.g. IES VE, Equest) to simulate baseline and predicted building energy performance as per methology of ASHRAE 90.1 Appendix G and show annual percentage savings. | D | Notes: Gray out and lock all the "D" sections
| Predicted | MWh/year
| Reduction | 20% | #DIV/0!
External lighting energy | Baseline (IECC 2009, Section 505.6) | MWh/year |  | Calculate external baseline and predicted annual energy use for lighting, exemptions include specialized event-related lighting like lightshows or displays
| Predicted | MWh/year
| Reduction | 20% | #DIV/0!
Landscape lighting energy | Baseline (IECC 2009, Section 505.6) | MWh/year |  | Calculate any landscape and/or pathway lighting baseline and predicted annual energy use
| Predicted | MWh/year
| Reduction | 50% | #DIV/0!
Produce Clean Energy (Design)
Renewable energy generated on site | Predicted enegy generation from onsite renewables | MWh/year |  | This is a site-wide KPI so not mandatory. However, if the pavilion is providing renewable energy (solar panels, micor wind turbines, etc) please indicate the capacity and offset savings from total consumption | D
Proportion of consumption offset by onsite renewable energy
WATER
Reduce Water Consumption (Design, Construction and During Event) |  |  |  | Notes:
Building water | Baseline (DEWA demand rates) | m³/day |  | Provide DEWA demand rate as per the Project Plot Sheet, and calculate savings from water-efficient fixtures, etc. | D
| Predicted Consumption | m³/day
| Reduction | 25% | #DIV/0!
Smart controls | Predicted | 100% |  | All main meters from DEWA are "smart," ensure any submeters are connected to BMS
Irrigation rates | Plot landscaping - Area | m² |  | Specify drought tolerant native and adaptive species to reduce irrigation water demand
| - Consumption | L/day
| - Rate | 4 | #DIV/0!
Total plot water consumption (design) | Overall prediction | m³/day | 0
Total plot water consumption (during construction and event) | DEWA potable water consumption | m³/month
| DM TSE water consumption | m³/month |  | TSE (Treated Sewage Effluent) is provided by DEWA for irrigation
Reuse Water (Design) |  |  |  | Notes:
Grey water treated and re-used on site |  | m³/day |  | Onsite greywater treatment systems can only be used for drip irrigation or dual flush toilets. | D
Condensate captured and reused on site |  | m³/day
Total volume of water that is reused (ie, has been treated since being created/made potable) |  | m³/day | 0
Potable water consumption avoided due to re-use of onsite generated grey water/condensate |  | % | #DIV/0!
MATERIALS
Recycle/Repurpose Materials |  |  |  | Notes:
Temporary: Total tonnage of material |  | t |  | Estimate of total materials from BOQ | D
Temporary: Tonnage of material designed for take-back/redeployment/recycling |  | t
Temporary: Percentage of temporary works designed for take-back/ redeployment/recycling |  | 75% | #DIV/0!
Use Sustainable Materials
Sustainable Material Guidelines | Total mass subject to SMG | t | Please fill in number | Sustainable Material Guidelines to be provided during construction | -1 |  | 40% | 0 | -1 | 0
Total mass of materials compliant with Guidelines | Predicted mass compliant | t | Please fill in number |  | 1 |  |  |  | 0 | 0.5
|  | 95% | 0% | Below 85% = RED; Between 85-95% = AMBER; 95% and above = GREEN. Weightage = 40% | 1 | Below 85% = RED; Between 85-95% = AMBER; 95% and above = GREEN. Weightage = 40% |  |  | 1 | 1
WASTE (Construction and During Event)
Quantities
Waste Quantities | Total | t/month | Please fill in number | Use waste logs during construction to demonstrate how much is diverted from landfill | -1 |  | 40% | 0
| Recycled | t/month | Please fill in number | Below 75% = RED; Between 75-85% = AMBER; 85% and above = GREEN. Weightage = 40% | 1
|  | 85% | 0% |  | 1 | Below 75% = RED; Between 75-85% = AMBER; 85% and above = GREEN. Weightage = 40%
EMISSIONS (Construction and During Event)
Site office generator diesel consumption |  | litres/month | Please fill in number |  | -1 |  | 20% | 0
Site plant fuel consumption |  | litres/month | Please fill in number |  | 1
Site vehicle fuel consumption |  | litres/month | Please fill in number |  | 1
Total site fuel consumption |  | litres/month | 0 |  | 1
Proportion of site fuel use provided by Biodiesel |  | 5% | Please fill in percentage | Below 5% = RED; 5% and above = GREEN. Weightage = 20% | 1 | Below 5% = RED; 5% and above = GREEN. Weightage = 20%
Electricity consumption (during event) |  | KWh/month | Please fill in number |  | 1
SITE, BIODIVERSITY, ECOLOGY (Design)
Proportion native/adaptive |  | 50% |  | By planted area | D
Minimum Number native/adaptive |  | 5
Number invasive |  | 0
PUBLIC REALM (Design)
Proportion shading | Pathways | 75% |  | Specific if there is no Public Realm design | D
| Open spaces | 60%
Heat Island Reduction strategies implemented |  | 70% |  | Heat Island strategies include high SRI roof and paving materials
SUSTAINABILTY AWARENESS (Design)
Proportion smart metering | Energy | 100% |  | Ensure meters and submeters are compatible with site-wide BMS system | D
| Water | 100%
Sustainability awareness displays |  | Yes
[7 empty] | 0% | -1

## Dashboard
[19 empty] | Planned | Overall Planned % | Overall Planned %
[20 empty] | Overall Actual % | Overall Actual %
[20 empty] | Planned % | Planned %
|  | 2019-10-22 | [17 empty] | Actual % | Actual %
Participant Monthly Dashboard
Please fill in
2019-10-22
Fact Sheet | [7 empty] | Key Issues |  | Project Overall Progress
[9 empty] | Issues: |  |  |  | Construction Progress RAG |  |  |  | #VALUE!
| Participant: | Please fill in |  | Participant Start date at site: |  |  | DD-MM-YY |  | Insert text
| Project Manager (PMC): | Please fill in |  | Project Finish (Readiness for auth. Inspec.) as per baseline: |  |  | DD-MM-YY | [5 empty] | This month |  | Cumulative |  | Variance
| Supervision Consultant: | Please fill in |  | Project Finish (Readiness for auth. Inspec.) as per update: |  |  | DD-MM-YY | [5 empty] | Planned | Actual | Planned | Actual
| Architect of Record (AOR): | Please fill in |  | Delays: |  |  | #VALUE! |  |  |  | Overall Progress |  | 0% | 0% | 0% | 0% | 0%
| Main Contractor: | Please fill in |  | Operation Fitness Certificate as per baseline: |  |  | DD-MM-YY
| Plot reference: | Please fill in |  | Operation Fitness Certificate as per latest update: |  |  | DD-MM-YY |  | Actions :
|  |  |  | Delays: |  |  | #VALUE! |  | Insert text | Milestones Updates
Executive Narrative Summary | [10 empty] | Milestone |  |  |  | Milestone date | Forecast / Actual | Variance
Insert text | [10 empty] | Concept Design Approval |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
[8 empty] | Participant Progress Charts |  |  | Final Design Approval |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
[11 empty] | Obtaining Plot Possession and Mobilising to site |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
[11 empty] | Obtaining Building Permit |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
[11 empty] | Shell and Core Completion (building weather tight) |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
[11 empty] | Readiness for Authorities Inspection |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
[11 empty] | Building Completion Certificate |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
[11 empty] | Operation Fitness Certificate |  |  |  | DD-MM-YY | DD-MM-YY | #VALUE!
Final Inspection Submission Status
Design and Permitting Status
[7 empty] | #VALUE! |  |  |  | Authority |  | Planned Date |  | Forecast / Actual |  | Variance
| Design | Concept Design status |  | Select from Drop Down List |  | 1 |  |  |  |  | Security Industry Regulatory Agency (SIRA) |  | DD-MM-YY |  | DD-MM-YY |  | #VALUE!
|  | Design change |  | Select from Drop Down List |  | 1 |  |  |  |  | Dubai Municipality (DM) |  | DD-MM-YY |  | DD-MM-YY |  | #VALUE!
|  | Final Design Status |  | Select from Drop Down List |  | 1 | Design progress RAG |  |  |  | Etisalat |  | DD-MM-YY |  | DD-MM-YY |  | #VALUE!
|  | Building Permit |  | Select from Drop Down List |  | 1 |  |  |  |  | Dubai Civil Defense (DCD) |  | DD-MM-YY |  | DD-MM-YY |  | #VALUE!
[11 empty] | Dubai Electricity and Water Authority (DEWA) - Water |  | DD-MM-YY |  | DD-MM-YY |  | #VALUE!
| Variance from Baseline | [9 empty] | Dubai South (DS) |  | DD-MM-YY |  | DD-MM-YY |  | #VALUE!
[11 empty] | Dubai Electricity and Water Authority (DEWA) - Electricity |  | DD-MM-YY |  | DD-MM-YY |  | #VALUE!
|  | Concept Design Approval |  |  |  | #VALUE!
|  | Final Design Approval |  |  |  | #VALUE! |  |  |  | Construction Progress by WBS
|  | Obtaining Building Permit |  |  |  | #VALUE!
[11 empty] | Stage / Area | Weight | This month |  | Cumulative |  | Variance
[13 empty] | Planned % | Actual % | Planned % | Actual %
Health Safety and Environment
I. Health and Safety: | [10 empty] | Mobilisation, Plot Pos, and Ground Works | 1.627% | #VALUE! | #VALUE! | Insert percentage | Insert percentage | #VALUE! |  | Insert percentage | Insert percentage
Insert text | [18 empty] | Insert percentage | Insert percentage
[11 empty] | Sub-Structure Works | 16.82% | #VALUE! | #VALUE! | Insert percentage | Insert percentage | #VALUE! |  | Insert percentage | Insert percentage
[11 empty] | Super-Structure Works | 21.41% | #VALUE! | #VALUE! | Insert percentage | Insert percentage | #VALUE! |  | Insert percentage | Insert percentage
[11 empty] | Façade | 12.23% | #VALUE! | #VALUE! | Insert percentage | Insert percentage | #VALUE! |  | Insert percentage | Insert percentage
[11 empty] | Finishes and MEP | 35.68% | #VALUE! | #VALUE! | Insert percentage | Insert percentage | #VALUE! |  | Insert percentage | Insert percentage
| Current |  |  |  |  | Cumulative | 1 |  |  |  | External works | 6.116% | #VALUE! | #VALUE! | Insert percentage | Insert percentage | #VALUE! |  | Insert percentage | Insert percentage
| Insert number |  | Fatalities |  | Insert number | [5 empty] | Testing and Commissioning | 6.116% | #VALUE! | #VALUE! | Insert percentage | Insert percentage | #VALUE! |  | 0% | 0%
| Insert number |  | Major Injuries |  | Insert number |  | H&S RAG
| Insert number |  | Over 3 Day Injuries |  | Insert number |  |  |  |  | Achieved Activities this month
| Insert number |  | Restricted Work Cases |  | Insert number |  |  |  |  | Insert text
| Insert number |  | Medical Treatment Injuries |  | Insert number
| Insert number |  | First Aid Injuries |  | Insert number
| #VALUE! |  | Near Miss & Non-injury incidents |  | #VALUE!
| Insert number |  | Participant Observations |  | Insert number
| Insert number |  | Work Hours |  | Insert number
II. Environment
Insert text
Planned Activities for next month
[8 empty] | Progress Photos |  | Insert text
#VALUE!
|  |  | Current | Cumulative
| Environment Minor Incidents |  | Insert number | Insert number |  |  | Env. RAG
| Environment Serious Incidents |  | Insert number | Insert number
Worker Welfare
Insert text | [6 empty] | -1 |  |  | Sustainibility
[10 empty] | Insert text | [6 empty] | -1
[7 empty] | WW RAG | [9 empty] | Sust. RAG
| Open Serious Non-Compliances (Not Overdue) |  |  |  | Insert number | [5 empty] | Sustainable materials usage ratio |  |  |  | 0%
| Overdue Serious Non-Compliances |  |  |  | Insert number | [5 empty] | Waste Recycled ratio |  |  |  | 0%
| Target Date to Close-Out all Open Serious Non-Compliances |  |  |  | DD-MM-YY | [5 empty] | Proportion of site fuel use provided by Biodiesel |  |  |  | Please fill in percentage
Non Conformance Statistics
#DIV/0!
[14 empty] | Raised | Closed | Opened (<4 days) | Opened (≥4 days)
[12 empty] | NCR |  | 46 | 35 | 0 | 11 | Env. RAG